## ActionsClean
Title | ActionTitle | Source | Location | Department | RiskLevel | Owner | DateRaised | DueDate | ActionStatus | DateClosed | RootCause
CA-001 | Replenish first aid cabinet | Inspection | Vessel Alpha | Procurement | Low | Master | 2026-08-24 | 2026-10-14 | Closed | 2026-09-04 | Poor documentation
CA-002 | Replace damaged lifeboat davit cover | Inspection | Vessel Bravo | Technical | Medium | Master | 2026-09-04 | 2026-10-14 | Closed | 2026-10-21 | Equipment wear
CA-003 | Improve housekeeping in engine room | Observation | Vessel Alpha | Procurement | High | Crewing Manager | 2026-08-01 | 2026-08-18 | Closed | 2026-09-10 | Unclear responsibility
CA-004 | Fix poor lighting at stairwell | Observation | Vessel Charlie | Procurement | Medium | Finance Lead | 2026-06-16 | 2026-07-23 | Closed | 2026-07-27 | Poor documentation
CA-005 | Replenish first aid cabinet | Inspection | Vessel Delta | Finance | High | Master | 2026-06-08 | 2026-06-23 | Closed | 2026-07-20 | Procedure not followed
CA-006 | Update emergency response procedure | Audit | Vessel Delta | Technical | Low | Procurement Lead | 2026-06-10 | 2026-07-30 | Open |  | Unclear responsibility
CA-007 | Revise contractor induction checklist | Audit | Vessel Delta | Finance | Medium | Chief Engineer | 2026-09-18 | 2026-10-16 | Closed | 2026-09-23 | Procedure not followed
CA-008 | Investigate near miss at mooring | Incident | Vessel Charlie | Finance | Medium | Finance Lead | 2026-06-13 | 2026-07-22 | Closed | 2026-06-24 | Training gap
CA-009 | Label chemical storage correctly | Observation | Shore Base PH | HSE | Medium | Chief Engineer | 2026-07-31 | 2026-09-07 | Closed | 2026-08-05 | Unclear responsibility
CA-010 | Clarify cargo hose test records | SIRE | Vessel Alpha | Operations | Medium | Finance Lead | 2026-06-05 | 2026-07-15 | Open |  | Equipment wear
CA-011 | Update emergency response procedure | Audit | Vessel Delta | Finance | Low | HSEQ Manager | 2026-07-08 | 2026-08-20 | Closed | 2026-07-13 | Training gap
CA-012 | Rectify SIRE observation on bridge log entries | SIRE | Vessel Alpha | HSE | High | Operations Manager | 2026-09-13 | 2026-10-04 | In Progress |  | Poor documentation
CA-013 | Replenish first aid cabinet | Inspection | Shore Base PH | Operations | Low | Chief Engineer | 2026-07-10 | 2026-09-03 | Closed | 2026-08-06 | Unclear responsibility
CA-014 | Revise contractor induction checklist | Audit | Vessel Bravo | Operations | Low | Chief Engineer | 2026-09-02 | 2026-10-25 | Closed | 2026-09-14 | Equipment wear
CA-015 | Review slip incident on gangway | Incident | Shore Base PH | Procurement | Medium | Chief Engineer | 2026-07-12 | 2026-08-11 | Open |  | Procedure not followed
CA-016 | Close gaps in permit-to-work records | Audit | Vessel Alpha | Finance | Low | Master | 2026-06-28 | 2026-08-10 | Closed | 2026-08-16 | Equipment wear
CA-017 | Label chemical storage correctly | Observation | Vessel Charlie | Technical | Low | Operations Manager | 2026-06-08 | 2026-07-27 | Closed | 2026-07-07 | Procedure not followed
CA-018 | Add signage at restricted area | Observation | Shore Base PH | Procurement | Low | Technical Superintendent | 2026-06-02 | 2026-07-20 | Closed | 2026-07-08 | Training gap
CA-019 | Update PPE issue register | Incident | Vessel Alpha | Operations | Medium | Finance Lead | 2026-09-06 | 2026-10-07 | In Progress |  | Procedure not followed
CA-020 | Close gaps in permit-to-work records | Audit | Shore Base PH | Operations | Medium | Finance Lead | 2026-08-17 | 2026-09-15 | Closed | 2026-09-03 | Unclear responsibility
CA-021 | Update emergency response procedure | Audit | Vessel Alpha | Finance | Medium | Chief Engineer | 2026-08-17 | 2026-09-25 | Closed | 2026-09-07 | Procedure not followed
CA-022 | Close gaps in permit-to-work records | Audit | Vessel Delta | Procurement | High | Chief Engineer | 2026-09-04 | 2026-09-24 | Open |  | Training gap
CA-023 | Revise contractor induction checklist | SIRE | Vessel Charlie | Finance | Low | Crewing Manager | 2026-08-01 | 2026-09-24 | Open |  | Procedure not followed
CA-024 | Update planned maintenance records | SIRE | Vessel Alpha | Operations | Low | Operations Manager | 2026-08-23 | 2026-10-17 | Closed | 2026-09-12 | Unclear responsibility
CA-025 | Update PPE issue register | Incident | Vessel Alpha | Crewing | High | Technical Superintendent | 2026-06-18 | 2026-06-29 | Closed | 2026-07-30 | Training gap
CA-026 | Repair deck handrail corrosion | Inspection | Vessel Alpha | Operations | High | Chief Engineer | 2026-08-29 | 2026-09-20 | Closed | 2026-09-14 | Unclear responsibility
CA-027 | Replace damaged lifeboat davit cover | Inspection | Vessel Charlie | Procurement | Medium | Operations Manager | 2026-08-12 | 2026-09-18 | Open |  | Unclear responsibility
CA-028 | Clarify cargo hose test records | SIRE | Vessel Delta | Finance | Low | Operations Manager | 2026-09-20 | 2026-11-13 | Closed | 2026-10-19 | Training gap
CA-029 | Replenish first aid cabinet | Inspection | Vessel Charlie | Crewing | Low | Chief Engineer | 2026-08-27 | 2026-10-19 | Open |  | Poor documentation
CA-030 | Fix poor lighting at stairwell | Observation | Vessel Delta | Finance | High | Procurement Lead | 2026-08-04 | 2026-08-19 | Closed | 2026-09-17 | Unclear responsibility
CA-031 | Investigate near miss at mooring | Incident | Vessel Delta | HSE | Medium | HSEQ Manager | 2026-09-20 | 2026-10-30 | Closed | 2026-09-24 | Procedure not followed
CA-032 | Retrain crew on lifting operations | Incident | Shore Base PH | HSE | Medium | Procurement Lead | 2026-06-21 | 2026-07-23 | Open |  | Poor documentation
CA-033 | Add signage at restricted area | Observation | Vessel Delta | Technical | Medium | Master | 2026-06-11 | 2026-07-19 | Open |  | Unclear responsibility
CA-034 | Improve housekeeping in engine room | Observation | Vessel Charlie | Crewing | High | Crewing Manager | 2026-06-14 | 2026-07-07 | Closed | 2026-07-03 | Poor documentation
CA-035 | Label chemical storage correctly | Observation | Vessel Bravo | Technical | Medium | Procurement Lead | 2026-07-21 | 2026-08-17 | Closed | 2026-08-03 | Unclear responsibility
CA-036 | Correct outdated fire drill schedule | Audit | Vessel Charlie | Operations | Low | Finance Lead | 2026-09-24 | 2026-11-12 | Open |  | Poor documentation
CA-037 | Investigate near miss at mooring | Incident | Vessel Charlie | Procurement | High | Crewing Manager | 2026-07-07 | 2026-07-23 | Closed | 2026-08-10 | Poor documentation
CA-038 | Investigate near miss at mooring | Incident | Vessel Delta | Finance | Medium | Crewing Manager | 2026-09-26 | 2026-10-28 | Open |  | Equipment wear
CA-039 | Calibrate gas detection unit | Inspection | Vessel Bravo | Technical | Low | Technical Superintendent | 2026-08-16 | 2026-10-07 | Closed | 2026-08-24 | Training gap
CA-040 | Correct outdated fire drill schedule | Audit | Vessel Delta | Procurement | Medium | Master | 2026-08-31 | 2026-10-01 | Open |  | Unclear responsibility
CA-041 | Correct outdated fire drill schedule | Audit | Vessel Charlie | Technical | Low | Unassigned | 2026-07-19 | 2026-08-30 | Open |  | Poor documentation
CA-042 | Fix chart correction log gaps | SIRE | Shore Base PH | HSE | Low | Unassigned | 2026-08-18 | 2026-09-30 | Closed | 2026-09-10 | Unclear responsibility
CA-043 | Revise contractor induction checklist | Audit | Vessel Charlie | Operations | Low | Technical Superintendent | 2026-07-05 | 2026-08-26 | Closed | 2026-07-24 | Training gap
CA-044 | Fix chart correction log gaps | SIRE | Vessel Delta | Finance | Low | HSEQ Manager | 2026-09-22 | 2026-11-07 | In Progress |  | Unclear responsibility
CA-045 | Review slip incident on gangway | Incident | Vessel Alpha | Procurement | High | Finance Lead | 2026-06-14 | 2026-07-07 | Closed | 2026-06-20 | Equipment wear
CA-046 | Update planned maintenance records | SIRE | Shore Base PH | Finance | Low | Operations Manager | 2026-08-30 | 2026-10-17 | Closed | 2026-09-28 | Poor documentation
CA-047 | Retrain crew on lifting operations | Incident | Vessel Alpha | HSE | Low | Chief Engineer | 2026-07-31 | 2026-09-24 | Closed | 2026-09-09 | Procedure not followed
CA-048 | Investigate near miss at mooring | Incident | Vessel Alpha | Technical | Low | Master | 2026-09-25 | 2026-11-16 | In Progress |  | Procedure not followed
CA-049 | Label chemical storage correctly | Observation | Shore Base PH | Technical | Medium | Crewing Manager | 2026-07-09 | 2026-08-12 | Open |  | Equipment wear
CA-050 | Revise contractor induction checklist | Audit | Shore Base PH | HSE | Medium | HSEQ Manager | 2026-08-25 | 2026-09-22 | Open |  | Poor documentation
CA-051 | Update PPE issue register | Incident | Shore Base PH | Operations | Low | Master | 2026-06-24 | 2026-08-17 | Open |  | Poor documentation
CA-052 | Add signage at restricted area | Observation | Vessel Delta | Crewing | Medium | Crewing Manager | 2026-07-16 | 2026-08-12 | Closed | 2026-08-08 | Equipment wear
CA-053 | Calibrate gas detection unit | Inspection | Vessel Bravo | Procurement | Low | HSEQ Manager | 2026-09-07 | 2026-10-23 | In Progress |  | Equipment wear
CA-054 | Replenish first aid cabinet | Inspection | Shore Base PH | Procurement | Medium | Master | 2026-06-07 | 2026-07-13 | Closed | 2026-07-03 | Equipment wear
CA-055 | Fix poor lighting at stairwell | Observation | Shore Base PH | HSE | Medium | Master | 2026-06-19 | 2026-07-25 | Closed | 2026-07-31 | Training gap
CA-056 | Label chemical storage correctly | Observation | Vessel Bravo | Operations | Medium | Unassigned | 2026-09-17 | 2026-10-20 | In Progress |  | Poor documentation
CA-057 | Fix chart correction log gaps | SIRE | Shore Base PH | HSE | Medium | HSEQ Manager | 2026-09-02 | 2026-10-04 | Closed | 2026-09-30 | Procedure not followed
CA-058 | Rectify SIRE observation on bridge log entries | SIRE | Shore Base PH | Operations | Medium | Chief Engineer | 2026-07-07 | 2026-08-06 | Closed | 2026-08-12 | Poor documentation
CA-059 | Investigate near miss at mooring | Incident | Vessel Bravo | Crewing | Low | Procurement Lead | 2026-06-29 | 2026-08-22 | Closed | 2026-07-13 | Procedure not followed
CA-060 | Add signage at restricted area | Observation | Vessel Alpha | Crewing | High | Crewing Manager | 2026-07-14 | 2026-08-04 | Closed | 2026-08-31 | Unclear responsibility
CA-061 | Improve housekeeping in engine room | Observation | Shore Base PH | Procurement | Low | HSEQ Manager | 2026-09-07 | 2026-10-23 | Closed | 2026-09-14 | Unclear responsibility
CA-062 | Calibrate gas detection unit | Inspection | Vessel Alpha | Operations | High | Chief Engineer | 2026-08-02 | 2026-08-18 | Closed | 2026-08-09 | Equipment wear
CA-063 | Revise contractor induction checklist | Audit | Shore Base PH | Procurement | Medium | HSEQ Manager | 2026-06-28 | 2026-07-25 | Closed | 2026-07-25 | Poor documentation
CA-064 | Fix chart correction log gaps | SIRE | Vessel Charlie | Crewing | Medium | Master | 2026-09-22 | 2026-10-27 | Open |  | Equipment wear
CA-065 | Clarify cargo hose test records | SIRE | Shore Base PH | HSE | Low | Operations Manager | 2026-08-08 | 2026-09-28 | Open |  | Equipment wear
CA-066 | Revise contractor induction checklist | Audit | Vessel Charlie | Finance | Low | Finance Lead | 2026-06-16 | 2026-07-31 | In Progress |  | Equipment wear
CA-067 | Label chemical storage correctly | Observation | Shore Base PH | Crewing | Medium | HSEQ Manager | 2026-09-23 | 2026-10-22 | Closed | 2026-10-06 | Unclear responsibility
CA-068 | Fix poor lighting at stairwell | Observation | Vessel Bravo | Procurement | Medium | Finance Lead | 2026-08-28 | 2026-10-06 | Closed | 2026-09-08 | Training gap
CA-069 | Review slip incident on gangway | Incident | Vessel Delta | Procurement | High | Technical Superintendent | 2026-08-19 | 2026-09-09 | Closed | 2026-09-10 | Equipment wear
CA-070 | Calibrate gas detection unit | Inspection | Vessel Bravo | Finance | Low | Operations Manager | 2026-07-28 | 2026-09-14 | Closed | 2026-08-09 | Procedure not followed
CA-071 | Rectify SIRE observation on bridge log entries | SIRE | Vessel Alpha | Finance | Medium | Finance Lead | 2026-09-11 | 2026-10-11 | Closed | 2026-10-06 | Unclear responsibility
CA-072 | Repair deck handrail corrosion | Inspection | Vessel Charlie | Technical | Medium | Procurement Lead | 2026-07-11 | 2026-08-14 | In Progress |  | Training gap
CA-073 | Correct outdated fire drill schedule | Audit | Vessel Charlie | Crewing | Medium | Procurement Lead | 2026-09-10 | 2026-10-13 | Closed | 2026-09-29 | Poor documentation
CA-074 | Fix chart correction log gaps | SIRE | Vessel Bravo | Finance | Low | Technical Superintendent | 2026-09-17 | 2026-11-11 | Closed | 2026-10-14 | Training gap
CA-075 | Update planned maintenance records | SIRE | Vessel Delta | Operations | Medium | Chief Engineer | 2026-09-04 | 2026-10-05 | Closed | 2026-10-04 | Poor documentation
CA-076 | Add signage at restricted area | Observation | Vessel Charlie | Procurement | Medium | Crewing Manager | 2026-06-01 | 2026-07-04 | In Progress |  | Training gap
CA-077 | Retrain crew on lifting operations | Incident | Vessel Bravo | Operations | Low | Operations Manager | 2026-06-05 | 2026-07-23 | Open |  | Poor documentation
CA-078 | Revise contractor induction checklist | Audit | Vessel Delta | Finance | High | HSEQ Manager | 2026-07-16 | 2026-08-05 | Closed | 2026-08-06 | Poor documentation
CA-079 | Retrain crew on lifting operations | Incident | Vessel Alpha | HSE | Low | Finance Lead | 2026-07-12 | 2026-08-31 | Closed | 2026-08-23 | Unclear responsibility
CA-080 | Revise contractor induction checklist | Audit | Vessel Bravo | Crewing | Medium | Chief Engineer | 2026-07-29 | 2026-09-02 | Open |  | Equipment wear
CA-081 | Fix chart correction log gaps | SIRE | Vessel Alpha | Procurement | Medium | Chief Engineer | 2026-09-04 | 2026-10-06 | Closed | 2026-09-19 | Poor documentation
CA-082 | Add signage at restricted area | Observation | Shore Base PH | Technical | High | HSEQ Manager | 2026-09-03 | 2026-09-14 | In Progress |  | Unclear responsibility
CA-083 | Calibrate gas detection unit | Inspection | Shore Base PH | Procurement | High | HSEQ Manager | 2026-08-13 | 2026-08-29 | Open |  | Unclear responsibility
CA-084 | Add signage at restricted area | Observation | Vessel Bravo | Finance | Low | Operations Manager | 2026-06-13 | 2026-08-04 | Closed | 2026-07-24 | Procedure not followed
CA-085 | Replace damaged lifeboat davit cover | Inspection | Vessel Charlie | Procurement | Medium | Finance Lead | 2026-06-27 | 2026-08-05 | Closed | 2026-08-12 | Procedure not followed
CA-086 | Repair deck handrail corrosion | Inspection | Vessel Charlie | Procurement | Low | Operations Manager | 2026-06-04 | 2026-07-18 | Closed | 2026-07-24 | Procedure not followed
CA-087 | Calibrate gas detection unit | Inspection | Shore Base PH | Procurement | High | Procurement Lead | 2026-07-12 | 2026-07-30 | Closed | 2026-07-23 | Unclear responsibility
CA-088 | Update PPE issue register | Incident | Vessel Delta | Technical | Medium | Chief Engineer | 2026-07-08 | 2026-08-04 | Closed | 2026-07-30 | Training gap
CA-089 | Update planned maintenance records | SIRE | Vessel Delta | Procurement | Medium | Technical Superintendent | 2026-07-04 | 2026-08-07 | Closed | 2026-08-21 | Equipment wear
CA-090 | Repair deck handrail corrosion | Inspection | Vessel Alpha | Finance | Medium | Finance Lead | 2026-09-19 | 2026-10-28 | In Progress |  | Unclear responsibility
CA-091 | Review slip incident on gangway | Incident | Shore Base PH | Procurement | Medium | Technical Superintendent | 2026-08-11 | 2026-09-09 | Open |  | Equipment wear
CA-092 | Improve housekeeping in engine room | Observation | Vessel Bravo | Crewing | High | Technical Superintendent | 2026-06-03 | 2026-06-26 | Closed | 2026-06-07 | Training gap
CA-093 | Add signage at restricted area | Observation | Vessel Alpha | Crewing | Low | Procurement Lead | 2026-07-07 | 2026-08-24 | Closed | 2026-08-16 | Equipment wear
CA-094 | Add signage at restricted area | Observation | Vessel Delta | Technical | Low | Technical Superintendent | 2026-07-05 | 2026-08-23 | Open |  | Equipment wear
CA-095 | Clarify cargo hose test records | SIRE | Vessel Charlie | Finance | Medium | Finance Lead | 2026-08-05 | 2026-09-14 | In Progress |  | Equipment wear
CA-096 | Update planned maintenance records | SIRE | Shore Base PH | Operations | Medium | Chief Engineer | 2026-08-22 | 2026-09-26 | Open |  | Unclear responsibility
CA-097 | Label chemical storage correctly | Observation | Vessel Charlie | Finance | Low | Crewing Manager | 2026-09-14 | 2026-11-02 | Closed | 2026-09-17 | Poor documentation
CA-098 | Improve housekeeping in engine room | Observation | Vessel Bravo | Technical | Low | Procurement Lead | 2026-07-29 | 2026-09-12 | In Progress |  | Procedure not followed
CA-099 | Calibrate gas detection unit | Inspection | Vessel Delta | HSE | Medium | Chief Engineer | 2026-07-22 | 2026-08-20 | Closed | 2026-08-17 | Unclear responsibility
CA-100 | Repair deck handrail corrosion | Inspection | Vessel Bravo | Finance | Medium | Master | 2026-09-09 | 2026-10-17 | In Progress |  | Unclear responsibility
CA-101 | Investigate near miss at mooring | Incident | Vessel Charlie | Finance | Low | Operations Manager | 2026-08-03 | 2026-09-22 | Closed | 2026-09-01 | Unclear responsibility
CA-102 | Add signage at restricted area | Observation | Vessel Bravo | Procurement | Low | HSEQ Manager | 2026-06-27 | 2026-08-12 | Open |  | Unclear responsibility
CA-103 | Calibrate gas detection unit | Inspection | Vessel Charlie | Finance | Low | HSEQ Manager | 2026-08-07 | 2026-09-23 | Closed | 2026-09-23 | Training gap
CA-104 | Update PPE issue register | Incident | Vessel Bravo | Technical | Medium | Master | 2026-08-31 | 2026-10-04 | Open |  | Unclear responsibility
CA-105 | Update PPE issue register | Incident | Vessel Bravo | Technical | High | Crewing Manager | 2026-07-15 | 2026-08-05 | Closed | 2026-08-21 | Poor documentation
CA-106 | Update emergency response procedure | Audit | Vessel Delta | Technical | Low | Master | 2026-07-28 | 2026-09-15 | Closed | 2026-08-20 | Equipment wear
CA-107 | Revise contractor induction checklist | Audit | Vessel Delta | Operations | Low | Chief Engineer | 2026-07-30 | 2026-09-20 | Closed | 2026-09-16 | Equipment wear
CA-108 | Review slip incident on gangway | Incident | Vessel Bravo | Operations | High | Master | 2026-09-15 | 2026-09-29 | Open |  | Unclear responsibility
CA-109 | Update emergency response procedure | Audit | Vessel Delta | Operations | High | Crewing Manager | 2026-09-14 | 2026-10-04 | Open |  | Training gap
CA-110 | Rectify SIRE observation on bridge log entries | SIRE | Shore Base PH | HSE | Medium | Finance Lead | 2026-07-04 | 2026-08-10 | Open |  | Training gap
CA-111 | Correct outdated fire drill schedule | Audit | Vessel Delta | Procurement | Medium | Finance Lead | 2026-08-18 | 2026-09-26 | Closed | 2026-09-17 | Poor documentation
CA-112 | Retrain crew on lifting operations | Incident | Vessel Charlie | HSE | Medium | Operations Manager | 2026-06-20 | 2026-07-30 | Closed | 2026-07-28 | Procedure not followed
CA-113 | Fix poor lighting at stairwell | Observation | Vessel Bravo | HSE | High | Finance Lead | 2026-09-10 | 2026-09-25 | Closed | 2026-10-21 | Procedure not followed
CA-114 | Update emergency response procedure | Audit | Vessel Charlie | Crewing | Medium | Technical Superintendent | 2026-09-09 | 2026-10-10 | In Progress |  | Equipment wear
CA-115 | Correct outdated fire drill schedule | Audit | Vessel Delta | Operations | Medium | Master | 2026-09-02 | 2026-09-29 | Open |  | Procedure not followed
CA-116 | Label chemical storage correctly | Observation | Vessel Delta | Finance | High | Finance Lead | 2026-07-07 | 2026-07-23 | Closed | 2026-07-19 | Equipment wear
CA-117 | Correct outdated fire drill schedule | Audit | Shore Base PH | Crewing | Medium | HSEQ Manager | 2026-08-21 | 2026-09-19 | Closed | 2026-10-05 | Procedure not followed
CA-118 | Update emergency response procedure | Audit | Vessel Delta | Operations | High | Finance Lead | 2026-09-12 | 2026-09-24 | Closed | 2026-10-02 | Unclear responsibility
CA-119 | Add signage at restricted area | Observation | Vessel Alpha | Operations | High | Operations Manager | 2026-09-08 | 2026-09-29 | Closed | 2026-09-29 | Unclear responsibility
CA-120 | Fix poor lighting at stairwell | Observation | Shore Base PH | Procurement | Medium | Procurement Lead | 2026-09-25 | 2026-10-27 | Closed | 2026-09-30 | Procedure not followed